Digital car switch panel

**October 2023**

**By**

**Thomas James Hammond**

**Student number 202112533**

**Word count: 2045**

Contents

[1. Project background and purpose 3](#_Toc149043049)

[1.1. Introduction 3](#_Toc149043050)

[1.2. Objectives 3](#_Toc149043051)

[Primary Objectives 3](#_Toc149043052)

[Secondary Objectives 3](#_Toc149043053)

[1.3. Requirements Capture 3](#_Toc149043054)

[1.4. Scope 4](#_Toc149043055)

[1.5. Deliverables 4](#_Toc149043056)

[1.6. Constraints 4](#_Toc149043057)

[1.7. Assumptions 4](#_Toc149043058)

[2. Project rationale and operation 5](#_Toc149043059)

[2.1. Project benefits 5](#_Toc149043060)

[2.2. Project operation 5](#_Toc149043061)

[2.3. Risk analysis 5](#_Toc149043062)

[2.4. Risk Matrix 5](#_Toc149043063)

[2.5. Risk Mitigation Plan 5](#_Toc149043064)

[2.6. Resources required 6](#_Toc149043065)

[3. Project methodology and outcomes 7](#_Toc149043066)

[3.1. Initial project plan 7](#_Toc149043067)

[3.1.1. Tasks and milestones 7](#_Toc149043068)

[3.1.2. Schedule Gantt chart 9](#_Toc149043069)

[3.2. Project control 10](#_Toc149043070)

[3.3. Project evaluation 10](#_Toc149043071)

[4. References 11](#_Toc149043072)

# Project background and purpose

## Introduction

The aim of the project is to give the user a digitized car switch board which will allow them to view digital gauges such as oil pressure, coolant temperature, boost pressure, mass air flow and per cylinder air volume. The user should be able to choose from some default gauges or they can add their own which will include variations on the design and the inputs available. The switch panel will also allow the user to turn on and off certain features just like a physical panel they can turn on accessories such as external lighting, fans, power kill switches and fuel pumps.

## Objectives

The project is useful as it will allow car enthusiasts to gain product which can give them much needed data and a switch panel which doesn’t take up much space on the dash and can be connected relatively easily. There currently isn’t much else on the market which would do the same and any that do are incredibly expensive or are built for specific cars which makes it hard to have a generalised product which can be used by everyone.

### Primary Objectives

The project will allow the user to view digital car gauges which will update in real time.

The project will allow the user to interact with the system via a touchscreen display.

The project will allow the user to click digital buttons which will control various car systems (e.g., fans or lighting)

The project should have large enough buttons that they can be pressed even when the road surface is making the car bumpy.

The project should not be distracting for the driver in any way.

### Secondary Objectives

The project will allow the user to change the background of gauges to their own liking.

The project will allow the user to connect to their car and view any errors the system has.

The project should have a fast start up time to ensure the usability of the devices as soon as the car is started.

## Requirements Capture

These are the initial requirements that will be set but further detailed requirements can be found in the requirements document.

* Interactive touchscreen display.
* Easy to use software which can be used by anyone no matter experience.
* Display 3 default gauges: coolant temperature, oil pressure, mass air flow.
* Allow users to change gauges to custom data inputs.
* Allow user to change background of gauges to any image.
* Display any error messages in a clear and easy format to read by the user.
* Keep the system plug and play by using 12v power.
* Display a digital switchboard which can control external systems added by the user. (Will display 3 toggle switches by default)
* Allow the user to upload or change the switch image type to one of their liking.
* System can run without any internet necessary.
* Can be run on main car groups without issues: Volkswagen, Ford, Audi, BMW
* There should be a menu which allow the user to change certain settings such as Bluetooth device connected, language or other accessibility options.

## Scope

The project will include switch control over some basic elements in the car such as fans, external lighting and power kill switches.

The project will display digital gauges such as oil pressure, coolant temperature, boost pressure and mass air flow.

The project will allow the user to customize the gauges with a custom image of their choice to make it personalised.

The project will allow the user to add their own sensors to the gauges.

## Deliverables

The project will deliver a program that can be run on a touchscreen display that will allow the user to control switches and view digital gauges. It will allow the user to quickly and easily control systems such as fans and external lighting. The gauges will update quickly and in real time to ensure the user is kept up to date with the latest data.

## Constraints

The project has a couple of constraints which could pose a problem. One of those issues is the fact that cars only have a 12v power supply and do not have mains voltage and therefore the project will have to keep in mind that the device will have to run off 12v. Another constraint is the Can system that the car uses to communicate with the device, this can be an issue as the Can system can vary between car models and will require specialised coding to ensure it is compatible with all vehicles and will communicate effectively.

## Assumptions

The project is assuming that the end user will have a basic knowledge of cars and will be able to locate a OBD2 port which will be used for the communication of data between the car and software.

# Project rationale and operation

## Project benefits

A successful project will allow car enthusiasts to have a device that will allow them to view gauges which would otherwise be unavailable to them such as oil pressure, turbo pressure or mass air flow. This extra information that the user will gain could help them to understand their car better and realise when they are at the limit of the car rather than breaking it as its been pushed too hard. The project will also allow car enthusiasts to have a much more compact switch board compared to physical switches which take up a lot of space.

## Project operation

I would use various forms of tracking including something such as a Trello board to monitor progress on specific tasks, gannet charts to make sure that timelines are being met and anything that is taking longer than expected to be monitored and changed on the charts as necessary.

## Risk analysis

Some risks within the project could include Time management, inaccurate estimation of tasks, Hardware failure or software failure. Due to the project being on a tight deadline this could cause it to run over the desired timeframe due to tasks being potentially under or overestimated in their amount of time it would take to complete. The project could also suffer from a few hardware failures such as screens breaking or components shorting out when testing new sensors. The project could also have software failures such as a CAN system authentication or decryption error which would lead to the system being unable to communicate with the car. The OBD device used could be limited in features available which could mean its harder to get the experience needed. The CAN system be different between different car models which could mean that it is incompatible and would require further development to enable to usage of the product.

## Risk Matrix

|  |  |  |  |
| --- | --- | --- | --- |
| Risk | Likelihood | Severity | Impact |
| Time Management | 2 | 3 | 2 x 3 = **6** |
| Inaccurate estimation of tasks | 2 | 2 | 1 x 2 = **4** |
| Hardware Failure | 1 | 4 | 1 x 4 = **4** |
| Software Failure | 1 | 1 | 1 x 1 = **1** |
| OBD Features | 1 | 4 | 1 x 4 = **4** |
| Incompatibility | 2 | 5 | 2 x 5 = **10** |

## Risk Mitigation Plan

|  |  |  |
| --- | --- | --- |
| Risk | How it will affect the project | Mitigation |
| Time Management | If time management is poor, it could affect how long the project will take for completion which could lead to the project being delayed | Multiple mid-way meetings should be held to determine the progress of the project and to see if it’s deemed to be behind schedule |
| Inaccurate estimation of tasks | If task completion time is not accurately recorded, then this could lead to some tasks taking much longer than anticipated or it could do the opposite and finish the project too early without adding any extra features therefore wasting time. | Tasks should be revied after to determine if a accurate time was given and then other similar tasks within the project should be update with a new estimated completion time |
| Hardware Failure | Hardware failure could include things such as then computer screen being broken or the circuit board being damaged or broken if any sensors short it out | Extra care should be taken when handling the screens and they can be stored in a safe bag which will help prevent any damages when not in use. When adding things such as sensors the system should be shut down and power disconnected to help prevent any short circuits. |
| Software Failure | Software failure could include decryption failure with the CAN system that could lead to the system not being able to connect to the car and gather data. | There isn’t any way to prevent this as it could be a random error that could occur |
| OBD Features | OBD device could be lacking features which could mean its harder to use and create the intended use case. | OBD research should be taken place to ensure that a device tat will deliver the required features are used. |
| Incompatibility | The system could be incompatible between different cars which could lead to uses being unable to use the product. | Research should be done into how the system could be make useable for all vehicles. Also have testing on various cars to help determine what cars are compatible and which are not. |

## Resources required

There is nothing specialised required to ensure the project runs smoothly and would only need some basic resources such as single board computer, touchscreen display and a OBD reader.

# Project methodology and outcomes

## Initial project plan

## Tasks and milestones

<https://view.monday.com/1287691726-a80fe9c0a5b5bfc890d920933efaeac2?r=euc1>


A screenshot of a computer

Description automatically generatedA screenshot of a computer

Description automatically generatedA screenshot of a computer

Description automatically generatedA screenshot of a computer

Description automatically generated

A screenshot of a computer

Description automatically generatedA screenshot of a computer

Description automatically generatedA screenshot of a computer

Description automatically generated

## Schedule Gantt chart

<https://view.monday.com/1287691726-df941cea98adf1a711a9b97a9bd9f919?r=euc1>

A screenshot of a computer

Description automatically generated

<https://view.monday.com/1287691726-02c521e8426240b3ef302d15d167be13?r=euc1>

A white grid with black and white text

Description automatically generated with medium confidence

A screenshot of a computer screen

Description automatically generated

## Project control

I will be using Trello to monitor the progress of tasks and keep track of what needs doing and how the project is progressing. By using Trello, it allows me to keep track of exactly what is going on in each sprint and what tasks are left in the backlog. I will be using a sprint system which will allow me to choose features from the backlog then work on them for a set amount of time then review what’s been done the repeat the process over and over. There wouldn’t be any real way of measuring progress other than seeing the physical prototype develop and become a much more useable object each time.

## Project evaluation

I will evaluate the success of the project in a few different ways; usability, user feedback and features delivered.

For the usability I will set up some test scenarios which would see the product being used such as how would it perform when going over a bumpy road, this will allow me to have a better understanding of how the delivered project works in the real world.

For the user feedback I would ask testers to fill in a questionnaire which will give them the opportunity to offer feedback on how the project has helped them and based off this I can compare it to what the project aimed to do and see if they match if so then it’s very likely that the project has succeeded.

For the features delivered evaluation I would look into what the project has been able to deliver compared to what the vison was and see if there are any big changes or features missing which would indicate success level of the project.

# References

<https://www.youtube.com/watch?v=SVn9uYfEQrA> - While researching for my project I found this very informative video of someone creating similar but instead of a switch panel it was being used purely just for a speed/tachometer.

<https://www.hackster.io/news/build-a-custom-dashboard-for-your-car-with-raspberry-pi-e66fbd46bb78> - This person used a raspberry pie which is relatively simple and inexpensive, and this helped to prove that a project of this would be possible and not just theory.